## milestones
Gantt template
Sub project 1 |  |  | Sub project 2 |  | Sub project 3 |  | Overall
No. | Projects | Milestones | Start date | Duration (Days) | End date | Remark
1 | Sub Project 1 | Requirement analysis | 2022-09-01 | 90 | 2022-11-30
2 |  | Expert review for system design | 2022-11-10 | 20 | 2022-11-30
3 |  | Software development | 2022-09-01 | 110 | 2022-12-20
4 |  | Internal test and bug fix | 2022-11-20 | 30 | 2022-12-20
5 |  | Deployment and launch | 2022-11-15 | 30 | 2022-12-15
6 |  | 3rd party test and bug fix | 2022-12-01 | 90 | 2023-03-01
7 |  | Security test and bug fix | 2022-11-01 | 40 | 2022-12-11
8 | Sub Project 2 | Requirement analysis | 2022-09-01 | 90 | 2022-11-30
9 |  | Expert review for system design | 2022-11-10 | 20 | 2022-11-30
10 |  | Software development | 2022-09-01 | 110 | 2022-12-20
11 |  | Internal test and bug fix | 2022-11-20 | 30 | 2022-12-20
12 |  | Deployment and launch | 2022-11-15 | 30 | 2022-12-15
13 |  | 3rd party test and bug fix | 2022-12-01 | 90 | 2023-03-01
14 |  | Security test and bug fix | 2022-11-01 | 40 | 2022-12-11
15 | Sub Project 3 | Internal test and bug fix | 2022-11-01 | 45 | 2022-12-16
16 |  | Deployment and launch | 2022-10-15 | 60 | 2022-12-14
17 |  | Security test and bug fix | 2022-10-25 | 50 | 2022-12-14
18 | Overall | Change request and audit | 2022-11-10 | 50 | 2022-12-30
19 |  | Document review & preliminary inspection | 2022-12-01 | 30 | 2022-12-31
20 |  | Make plans & execution of trainings | 2022-12-20 | 70 | 2023-02-28
21 |  | Solution & plans of operation & maintenance | 2023-02-01 | 50 | 2023-03-23
22 |  | Pilot run, adjustment on preliminary inspection | 2022-12-20 | 90 | 2023-03-20
23 |  | Finalize documents & documents inspection | 2023-02-01 | 50 | 2023-03-23
24 |  | Financial audit | 2023-02-01 | 40 | 2023-03-13
25 |  | Financial inspection | 2023-02-10 | 40 | 2023-03-22
26 |  | Final review & inspection of whole project | 2023-03-01 | 30 | 2023-03-31
说明：填完时间规划后，请先设置最标轴的最小值为44805,最大值为45016，图表坐标轴日期即可自动调整（这两个数字是根据您填写的时间自动变化的）
Formulas:
Sub project 3 = [Sub project 2]+[Duration (Days)]

## schedules
Year |  | 2022 | [13 empty] | 2023
Quarter |  | / | Quarter 4 | [12 empty] | Quarter 1
Month |  | Sep. & before | Oct. |  |  |  | Nov. |  |  |  | Dec. |  |  |  |  | Jan. |  |  |  |  | Feb. |  |  |  | Mar.
Week |  | / | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Day |  | / | 1 9 | 10 16 | 17 23 | 24 31 | 1 6 | 7 13 | 14 20 | 21 30 | 1 4 | 5 11 | 12 18 | 19 25 | 26 31 | 1 8 | 9 15 | 16 22 | 23 29 | 30 31 | 1 5 | 6 12 | 13 19 | 20 28 | 1 5 | 6 12 | 13 19 | 20 26 | 27 31
Project | Milestones
Sub Project 1 | Requirement analysis
Expert review for system design
Software development
Internal test and bug fix
deployment and launch
3rd party test and bug fix
Security test and bug fix
Sub Project 2 | Requirement analysis
Expert review for system design
Software development
Internal test and bug fix
deployment and launch
3rd party test and bug fix
Security test and bug fix
Sub Project 3 | Internal test and bug fix
deployment and launch
Security test and bug fix
Overall | Change request and audit
Document review & preliminary inspection
Make plans & execution of trainings
Solution & plans of operation and maintenance
Pilot run, adjustment on preliminary inspection
Finalize documents & documents inspection
Financial audit
Financial inspection
Final review & inspection of whole project